## Priorities 1-3
Results Focused Transition Framework (RFTF)
Water and Sanitation Priority Sector
Key Priorities, Outcomes, Benchmarks & Funding Requirements 2004 - 2005
Months | January - June 2004 |  | July - December 2004 |  | Total 2004 | January - June 2005 |  | July - December 2005 |  | Total 2005 | Total '04-'05
| qualitative | US$ (mln) | qualitative | US$ (mln) | US$ (mln) | qualitative | US$ (mln) | qualitative | US$ (mln) | US$ (mln) | US$ (mln)
Priority 1: Strengthen governance, co-ordination, revenue control and transparency. | Indentify external consultant and start review of State systems. Identify and place two external fulltime consultants within operational WatSan Manangement structure. |  | Complete State review, agree on best option, start to impliment changes. Two fulltime consultants in place. Two visiting expert trips. 20 key WatSan managers to start management day release or correspondence training. |  |  | Complete State structure changes. Two full time consultants in place. Two visiting expert trips. |  | Two full time consultants in place. 20 key WatSan managers to finish management day release or correspondence training.
I - Key outcome: Sustainable State WatSan related structures and proceedures will have been established.
II - Key progress benchmark
III - Financial Requirements
a) Capital Investments |  | 0 |  | 0.52 | 0.52 |  | 0.52 |  | 0 | 0.52 | 1.04
b) Incremental Recurrent Expenditures |  | 0.01 |  | 0.05 | 0.06 |  | 0.05 |  | 0 | 0.05 | 0.11
c) Technical Assistance |  | 0.27 |  | 0.42 | 0.69 |  | 0.25 |  | 0.25 | 0.5 | 1.19
Total Financial Requirements Priority 1 |  | 0.28 |  | 0.99 | 1.27 |  | 0.82 |  | 0.25 | 1.07 | 2.34
Annual average total staff priority 1 |  |  |  |  | Zero staff |  |  |  |  | Zero staff
|  | 0 |  |  |  |  | 0
Priority 2: Strengthen Monrovia's managed water system. | Two new water test labs. Complete one needs asses't of Monrovia water options. Maintain 6,000m3/day water production. Reduce, in overall percentage terms, levels of ‘unaccounted’ for water. |  | Increase Monrovia water production to 8,000m3/day. Further reduce, in overall percentage terms, levels of ‘unaccounted’ for water. |  |  | Increase Monrovia water production to 12,000m3/day. Further reduce, in overall percentage terms, levels of ‘unaccounted’ for water. |  | Increase Monrovia water production to 18,000m3/day. Further reduce, in overall percentage terms, levels of ‘unaccounted’ for water.
I - Key outcome: Sustainable managed water production in Monrovia will have trebled.
II - Key progress benchmark
III - Financial Requirements
a) Capital Investments |  | 0.6 |  | 0.8 | 1.4 |  | 0.6 |  | 0.3 | 0.9 | 2.3
b) Incremental Recurrent Expenditures |  | 0.5 |  | 0.75 | 1.25 |  | 1 |  | 1.2 | 2.2 | 3.45
c) Technical Assistance |  | 0.04 |  | 0.01 | 0.05 |  | 0.01 |  | 0 | 0.01 | 0.06
Total Financial Requirements Priority 2 |  | 1.14 |  | 1.56 | 2.7 |  | 1.61 |  | 1.5 | 3.11 | 5.81
Annual average total staff priority 2 |  |  |  |  | 75 staff |  |  |  |  | 94 staff
Priority 3: Strengthen Monrovia's managed sewage system. | Complete one rapid needs asses't of Monrovia emergency sewage water options. Establish safe disposal location for sewerage tankers |  | No sewage overflows in populated areas. Start one technical needs asses't of Monrovia medium and long term sewage water options |  |  | No sewage overflows onto streets. Complete one technical needs asses't of Monrovia medium and long term sewage water options. |  | No sewage overflows onto streets. Complete outline design for Monrovia's prefered medium term sewage option.
I - Key outcome: Systems for sustainable eradication of sewage contamination in populated areas established.
II - Key progress benchmark
III - Financial Requirements
a) Capital Investments |  | 0.7 |  | 1.7 | 2.4 |  | 1 |  | 0.1 | 1.1 | 3.5
b) Incremental Recurrent Expenditures |  | 0.2 |  | 0.2 | 0.4 |  | 0.2 |  | 0.2 | 0.4 | 0.8
c) Technical Assistance |  | 0.03 |  | 0.04 | 0.07 |  | 0.04 |  | 0.2 | 0.24 | 0.31
Total Financial Requirements Priority 3 |  | 0.93 |  | 1.94 | 2.87 |  | 1.24 |  | 0.5 | 1.74 | 4.61
Annual average total staff priority 3 |  |  |  |  | 20 staff |  |  |  |  | 30 staff
Total Financial Requirements for above priorities
a) Capital Investments |  | 1.3 |  | 3.02 | 4.32 |  | 2.12 |  | 0.4 | 2.52 | 6.84
b) Incremental Recurrent Expenditures |  | 0.71 |  | 1 | 1.71 |  | 1.25 |  | 1.4 | 2.65 | 4.36
c) Technical Assistance |  | 0.34 |  | 0.47 | 0.81 |  | 0.3 |  | 0.45 | 0.75 | 1.56
Grand Total Financial Requirements for above priorities |  | 2.35 |  | 4.49 | 6.84 |  | 3.67 |  | 2.25 | 5.92 | 12.76
Grand Total annual average staff for above priorities |  |  |  |  | 95 staff |  |  |  |  | 124 staff | 109.5 staff

## Priorities 4-6
Results Focused Transition Framework (RFTF)
Water and Sanitation Priority Sector
Key Priorities, Outcomes, Benchmarks & Funding Requirements 2004 - 2005
Months | January - June 2004 |  | July - December 2004 |  | Total 2004 | January - June 2005 |  | July - December 2005 |  | Total 2005 | Total '04-'05
| qualitative | US$ (mln) | qualitative | US$ (mln) | US$ (mln) | qualitative | US$ (mln) | qualitative | US$ (mln) | US$ (mln) | US$ (mln)
Priority 4: Provide urban managed water and solid waste disposal systems (not Monrovia). | Complete two water and two solid waste assessments and designs. |  | Establish two urban water and solid waste systems to serve 70k people. Complete two water and two waste assessments and designs. |  |  | Establish two urban water and solid waste systems to serve 70k people. Complete two water and two waste assessments and designs. |  | Establish two urban water and solid waste systems to serve 70k people.
I - Key outcome: Six sustainable managed urban water and solid waste disposal systems will have been established.
II - Progress benchmark
III - Financial Requirements
a) Capital Investments |  | 0.1 |  | 1.44 | 1.54 |  | 1.44 |  | 1.44 | 2.88 | 4.42
b) Incremental Recurrent Expenditures |  | 0.05 |  | 0.2 | 0.25 |  | 0.45 |  | 0.7 | 1.15 | 1.4
c) Technical Assistance |  | 0.1 |  | 0.1 | 0.2 |  | 0.1 |  | 0 | 0.1 | 0.3
Total Financial Requirements Priority 4 |  | 0.25 |  | 1.74 | 1.99 |  | 1.99 |  | 2.14 | 4.13 | 6.12
Annual average total staff priority 4 |  |  |  |  | 45 staff |  |  |  |  | 150 staff
|  | 0 |  |  |  |  | 0
Priority 5: Strengthen Monrovia's managed solid waste disposal and surface water drainage systems. | Identify two solid waste sites. Establish one new solid waste site. Ten bin trucks purchased. All surface water drains kept clear and free of blockages. All solid waste cleared away within one week. |  | Establish one new solid waste site if required. All surface water drains kept clear and free of blockages. All solid waste cleared away within one week. |  |  | Ten bin trucks purchased if required. All surface water drains kept clear and free of blockages. All solid waste cleared away within one week. |  | All surface water drains kept clear and free of blockages. All solid waste cleared away within one week.
I - Key outcome: Sustainable managed waste disposal and surface water system will have been established in Monrovia.
II - Progress benchmark
III - Financial Requirements
a) Capital Investments |  | 2.15 |  | 0.95 | 3.1 |  | 1.15 |  | 0 | 1.15 | 4.25
b) Incremental Recurrent Expenditures |  | 0.25 |  | 0.98 | 1.23 |  | 0.98 |  | 0.98 | 1.96 | 3.19
c) Technical Assistance |  | 0.02 |  | 0.02 | 0.04 |  | 0.05 |  | 0.05 | 0.1 | 0.14
Total Financial Requirements Priority 5 |  | 2.42 |  | 1.95 | 4.37 |  | 2.18 |  | 1.03 | 3.21 | 7.58
Annual average total staff priority 5 |  |  |  |  | 180 staff |  |  |  |  | 240 staff
Priority 6: Strengthen Monrovia's community based Water and excreta disposal facilities. | Household water treat' campaign that informs 90% of the population who rely on non-managed water supplies. Rehab 400 wells. Rehab or build 400 drop holes. Build five enhanced public sanitation blocks. |  | 30% of population who rely on non-managed water supplies regularly carry out household water treatment. Rehab 700 wells.Rehab or build 760 drop holes. Build five enhanced public sanitation blocks. |  |  | 50% of population who rely on non-managed water supplies regularly carry out household water treatment. Rehab 700 wells. Rehab or build 760 drop holes. |  | 75% of population who rely on non-managed water supplies regularly carry out household water treatment. Rehab 700 wells. Rehab or build 760 drop holes.
I - Key outcome: Improved levels of community based water wells and latrines will be established in Monrovia.
II - Progress benchmark
III - Financial Requirements
a) Capital Investments |  | 0.83 |  | 0.96 | 1.79 |  | 0.93 |  | 0.93 | 1.86 | 3.65
b) Incremental Recurrent Expenditures |  | 0.01 |  | 0.03 | 0.04 |  | 0.03 |  | 0.03 | 0.06 | 0.1
c) Technical Assistance |  | 0.01 |  | 0.01 | 0.02 |  | 0 |  | 0 | 0 | 0.02
Total Financial Requirements Priority 6 |  | 0.85 |  | 1 | 1.85 |  | 0.96 |  | 0.96 | 1.92 | 3.77
Annual average total staff priority 6 |  |  |  |  | 150 staff |  |  |  |  | 150 staff
Total Financial Requirements for above priorities
a) Capital Investments |  | 3.08 |  | 3.35 | 6.43 |  | 3.52 |  | 2.37 | 5.89 | 12.32
b) Incremental Recurrent Expenditures |  | 0.31 |  | 1.21 | 1.52 |  | 1.46 |  | 1.71 | 3.17 | 4.69
c) Technical Assistance |  | 0.13 |  | 0.13 | 0.26 |  | 0.15 |  | 0.05 | 0.2 | 0.46
Grand Total Financial Requirements for above priorities |  | 3.52 |  | 4.69 | 8.21 |  | 5.13 |  | 4.13 | 9.26 | 17.47
Grand Total annual average staff for above priorities |  |  |  |  | 375 staff |  |  |  |  | 540 staff | 457.5 staff

## Priorities 7-8
Results Focused Transition Framework (RFTF)
Water and Sanitation Priority Sector
Key Priorities, Outcomes, Benchmarks & Funding Requirements 2004 - 2005
Months | January - June 2004 |  | July - December 2004 |  | Total 2004 | January - June 2005 |  | July - December 2005 |  | Total 2005 | Total '04-'05
| qualitative | US$ (mln) | qualitative | US$ (mln) | US$ (mln) | qualitative | US$ (mln) | qualitative | US$ (mln) | US$ (mln) | US$ (mln)
Priority 7: Strengthen urban (non-Monrovia) community based Water and excreta disposal facilities. | Household water treat' campaign that informs 90% of the population in six urban areas who rely on non-managed water supplies. Rehab 300 wells. Rehab or build 1200 drop holes. Build two water test labs. 1 new drilling rig. |  | 30% of population in the six urban areas who rely on non-managed water supplies regularly carry out household water treatment. Rehab 500 wells.Rehab or build 2000 drop holes. Build four water test labs. |  |  | 50% of population in the six urban areas who rely on non-managed water supplies regularly carry out household water treatment. Rehab 500 wells. Rehab or build 2000 drop holes. |  | 75% of population in the six urban areas who rely on non-managed water supplies regularly carry out household water treatment. Rehab 500 wells. Rehab or build 2000 drop holes.
I - Key outcome: Improved levels of community based water wells and latrines will be established in urban areas.
II - Progress benchmark
III - Financial Requirements
a) Capital Investments |  | 1.42 |  | 1.65 | 3.07 |  | 1.44 |  | 1.44 | 2.88 | 5.95
b) Incremental Recurrent Expenditures |  | 0.06 |  | 0.08 | 0.14 |  | 0.08 |  | 0.08 | 0.16 | 0.3
c) Technical Assistance |  | 0.21 |  | 0.01 | 0.22 |  | 0.01 |  | 0.01 | 0.02 | 0.24
Total Financial Requirements Priority 7 |  | 1.69 |  | 1.74 | 3.43 |  | 1.53 |  | 1.53 | 3.06 | 6.49
Annual average total staff priority 7 |  |  |  |  | 480 staff |  |  |  |  | 480 staff
|  | 0 |  |  |  |  | 0
Priority 8: Strengthen rural community based Water and excreta disposal facilities. | Establish a centralised data base to record available information on the WatSan situation in rural areas. Rehab 500 wells. Build 100 wells. Build 1000 drop holes. Purchase two drilling rigs. |  | Rehab 1500 wells. Build 150 wells. Build 2000 drop holes. |  |  | Build 250 wells. Build 3000 drop holes. |  | Build 250 wells. Build 3000 drop holes.
I - Key outcome: Improved levels of community based water wells and latrines will be established in rural areas.
II - Progress benchmark
III - Financial Requirements
a) Capital Investments |  | 2.3 |  | 2.6 | 4.9 |  | 0.7 |  | 0.7 | 1.4 | 6.3
b) Incremental Recurrent Expenditures |  | 0.1 |  | 0.1 | 0.2 |  | 0.1 |  | 0.1 | 0.2 | 0.4
c) Technical Assistance |  | 0.03 |  | 0.03 | 0.06 |  | 0.03 |  | 0.03 | 0.06 | 0.12
Total Financial Requirements Priority 8 |  | 2.43 |  | 2.73 | 5.16 |  | 0.83 |  | 0.83 | 1.66 | 6.82
Annual average total staff priority 8 |  |  |  |  | 330 staff |  |  |  |  | 330 staff
Total Financial Requirements for above priorities
a) Capital Investments |  | 3.72 |  | 4.25 | 7.97 |  | 2.14 |  | 2.14 | 4.28 | 12.25
b) Incremental Recurrent Expenditures |  | 0.16 |  | 0.18 | 0.34 |  | 0.18 |  | 0.18 | 0.36 | 0.7
c) Technical Assistance |  | 0.24 |  | 0.04 | 0.28 |  | 0.04 |  | 0.04 | 0.08 | 0.36
Grand Total Financial Requirements for above priorities |  | 4.12 |  | 4.47 | 8.59 |  | 2.36 |  | 2.36 | 4.72 | 13.31
Grand Total annual average staff for above priorities |  |  |  |  | 810 staff |  |  |  |  | 810 staff | 810 staff