## Summary
Labor
INTEGRATION | 2160000
Segments
DATA TRANSPORT | 4606800
METADATA AND DISCOVERY | 4972725
DATA ARCHIVE AND ACCESS | 4892250
Total Labor | 16631775
Infrastructure | 19300000
Total DMAC | 35931775

## Labor
Item | Task | Staffing | % time | Duration (m) | Rate | Unit Cost | Units | Cost
INTEGRATION |  | 6 | 0.5 | 48 | 15000 |  | 3 | 2160000
Segments
DATA TRANSPORT
Requirement: Develop Comprehensive IOOS Data Model
Milestone 1: Develop Comprehensive Data Model
| Task 1: Convene IOOS Data Model Working Group | 6 | 0.1 | 6 | 15000 |  | 0.6 | 54000
| Task 2: Develop data models for all classes of ocean data | 6 | 0.2 | 21 | 15000 |  | 1.2 | 378000
| Task 3: Synthesize the work of Task 1 into a uniform model (or small suite of models) | 3 | 0.15 | 15 | 15000 |  | 0.45 | 101250
| Task 4: Pilot implementations of data model | 4 | 0.25 | 21 | 15000 |  | 1 | 315000
| Task 5: Develop controlled vocabularies | 4 | 0.1 | 12 | 15000 |  | 0.4 | 72000
| Task 6: Publish draft data model – follow IOOS Standards Process for Review | 4 | 0.1 | 10 | 15000 |  | 0.4 | 60000
Requirement: Deliver time-critical (real-time) data to data assembly and operational modeling sites
Milestone 1: Provide operational support for time-critical data
| Task 1: Adopt Unidata IDD as initial, provisional, fast-track transport solution | 1 | 0.25 | 12 | 15000 |  | 0.25 | 45000
| Task 2: Determine evaluation and review process to be followed for Unidata IDD | 2 | 0.25 | 2 | 15000 |  | 0.5 | 15000
| Task 3: Evaluate the state of real-time data access to current and potential modeling operational sites. | 4 | 0.25 | 6 | 15000 |  | 1 | 90000
| Task 4: Identify IOOS partner sites to serve as real-time data assembly and distribution centers | 2 | 0.005 | 38 | 15000 |  | 0.01 | 5700
| Task 5: Initiate complimentary and/or alternative real-time delivery solutions | 2 | 0.1 | 15 | 15000 |  | 0.2 | 45000
| Task 6: Explore blended Push/Pull delivery | 2 | 0.1 | 12 | 15000 |  | 0.2 | 36000
Requirement: Develop DMAC Middleware
Milestone 1: Survey and prioritize data management solutions in use by IOOS data suppliers.
| Task 1: Survey the IOOS participants to determine what must be addressed by the middleware, and the particular data sets. | 3 | 0.1 | 12 | 15000 |  | 0.3 | 54000
| Task 2: Prioritize the server-side requirements based on IOOS theme priorities and critical data streams | 3 | 0.1 | 6 | 15000 |  | 0.3 | 27000
| Task 3: Initiate development of server-side solutions based upon priorities | 3 | 0.5 | 20 | 15000 |  | 1.5 | 450000
Milestone 2: Survey and prioritize legacy and new client applications that should be supported.
| Task 1: Survey user groups (and potential ocean information product suppliers) to access application and formatted file needs | 1 | 0.2 | 12 | 15000 |  | 0.2 | 36000
| Task 2: Prioritize the client-side requirements based on IOOS theme priorities and critical data streams | 1 | 0.2 | 9 | 15000 |  | 0.2 | 27000
| Task 3: Initiate development of application solutions and downloadable formats based upon priorities | 2 | 0.5 | 12 | 15000 |  | 1 | 180000
Milestone 3: Determine the specification for the ODAP
| Task 1: Adopt OPeNDAP as initial, provisional fast-track transport solution | 3 | 0.2 | 12 | 15000 |  | 0.6 | 108000
| Task 2: Publish draft OPeNDAP specification document. Request comments. | 2 | 0.2 | 2 | 15000 |  | 0.4 | 12000
| Task 3: Determine evaluation and review process to be followed for OPeNDAP | 2 | 0.25 | 2 | 15000 |  | 0.5 | 15000
| Task 4: Initiate complimentary and/or alternative ODAP solutions | 4 | 0.2 | 12 | 15000 |  | 0.8 | 144000
| Task 5: Develop an ancillary information framework allowing OPeNDAP servers to convert the native structure | 4 | 0.2 | 15 | 15000 |  | 0.8 | 180000
| Task 6: Develop requirements and software specifications, followed by design and implement of the aggregation serversons . | 3 | 0.5 | 12 | 15000 |  | 1.5 | 270000
Requirement: Make data available using IOOS middleware solution
Milestone 1: Ensure that IOOS data suppliers make data available through middleware
| Task 1: Train middleware installers/troubleshooters/trainers | 2 | 0.05 | 33 | 15000 |  | 0.1 | 49500
| Task 2: Install middleware adaptors and other software as needed at suppliers sites | 2 | 0.05 | 33 | 15000 |  | 0.1 | 49500
Requirement: Data Manipulation Services
Milestone 1: Prioritize and Implement Data Manipulation Services
| Task 1: Prioritize Data Manipulation Services | 2 | 0.1 | 12 | 15000 |  | 0.2 | 36000
| Task 2: Develop specifications and implement services | 4 | 0.25 | 21 | 15000 |  | 1 | 315000
Requirement: Develop Metrics and Implement Performance Monitoring
Milestone 1: Determine specifications for Metrics and Performance Monitoring
| Task 1: Determine metrics to be used in DMAC and requirements for performance monitoring | 2 | 0.1 | 9 | 15000 |  | 0.2 | 27000
| Task 2: Implement performance monitoring in DMAC systems | 1 | 0.01 | 24 | 15000 |  | 0.01 | 3600
| Task 3: Pre-operational | 1 | 0.25 | 15 | 15000 |  | 0.25 | 56250
Requirement: Implement Middleware Security (Cross-discipline effort with all DMAC)
Milestone 1: Create middleware Security Plan
| Task 1: Determine Data Transport Security needs with DMAC | 1 | 0.25 | 12 | 15000 |  | 0.25 | 45000
Milestone 2: Develop and deploy middleware Security Plan
Requirement: Data Subscription Services
Milestone 1: Provide data subscription service support
| Task 1: [flesh out] | 2 | 0.25 | 12 | 15000 |  | 0.5 | 90000
| Task 2: Optional Push/Pull delivery | 2 | 0.25 | 12 | 15000 |  | 0.5 | 90000
| Task 3: Pilot Task with DAP | 2 | 0.25 | 12 | 15000 |  | 0.5 | 90000
Requirement: Provide guaranteed geo-temporal-referenced browse for all IOOS data
Milestone 1: Guaranteed minimum geo-temporally referenced graphics and numeric listings
| Task 1: Adopt the NVODS Live Access Server (LAS) as initial, provisional, fast-track guaranteed minimum browse solution | 2 | 0.1 | 15 | 15000 |  | 0.2 | 45000
| Task 2: Determine evaluation and review process to be followed for OPeNDAP | 2 | 0.1 | 6 | 15000 |  | 0.2 | 18000
| Task 3:Initiate complimentary and/or alternative real-time delivery solutions | 4 | 0.15 | 36 | 15000 |  | 0.6 | 324000
| Task 4: Determine the suite of visualization styles and file formats and data comparison capabilities | 4 | 0.15 | 36 | 15000 |  | 0.6 | 324000
| Task 5: Implement additional visualization styles and file formats and data comparison capabilities as determined | 4 | 0.15 | 36 | 15000 |  | 0.6 | 324000
Total for Data Transport | [6 empty] | 4606800
Item | Task | Staffing | % time | Duration (m) | Rate | Unit Cost | Units | Cost
METADATA AND DISCOVERY
Requirement: Metadata: Determine IOOS Metadata Content and Format Standards
Milestone 1: Compile an initial list of IOOS metadata standards
| Task 1: Convene a DMAC working group to do preliminary assessment of metadata standards from FGDC etc. | 6 | 0.25 | 4.4 | 15000 |  | 1.5 | 99000
Milestone 2: Compile an Interim IOOS Metadata Standards
| Task 1: Convene an IOOS Metadata Standards Working Group. | 3 | 0.25 | 3 | 15000 |  | 0.75 | 33750
| Task 2: Establish Liaison with metadata standards groups like FGDC. | 2 | 0.25 | 4.4 | 15000 |  | 0.5 | 33000
| Task 3: Make interim list of keywords and a data dictionary | 3 | 0.25 | 14 | 15000 |  | 0.75 | 157500
| Task 4: Study use of thesauri to enable machine-to-machine interoperability with semantic meaning. | 2 | 0.25 | 14 | 15000 |  | 0.5 | 105000
| Task 5: W/G incorporates input from expert subcommittees, results of studies, R&D, pilots, etc. into Interim Standards. | 3 | 0.2 | 14 | 15000 |  | 0.6 | 126000
Milestone 3: Determine specifications for adaptability of metadata associated with transported data.
| Task 1: Determine metadata modification for subsetted data | 4 | 0.25 | 4.4 | 15000 |  | 1 | 66000
| Task 2: Determine metadata modification for aggregated data | 4 | 0.25 | 4.4 | 15000 |  | 1 | 66000
| Task 3: Determine metadata modification requirements for products or merged data. | 4 | 0.25 | 4.4 | 15000 |  | 1 | 66000
Milestone 4: Determine Specifications for Data Quality metadata
| Task 1: Working Group with DMAC to determine Data Quality Metadata specifications. | 4 | 0.25 | 6.6 | 15000 |  | 1 | 99000
| Task 2: Determine how data lineage should be reported in metadata. | 2 | 0.2 | 2 | 15000 |  | 0.4 | 12000
Requirement: Develop Tools and Procedures to Support Metadata Providers
Milestone 1: Develop and Maintain Metadata
| Task 1: Select or develop a master metadata management system | 4 | 0.25 | 8.7 | 15000 |  | 1 | 130500
| Task 2: Develop/acquire tools for metadata generation, validation, maintenance. | 3 | 0.5 | 8.7 | 15000 |  | 1.5 | 195750
| Task 3: Provide developer support to users. | 4 | 0.5 | 8.7 | 15000 |  | 2 | 261000
| Task 4: Plan regular reviews of exiting metadata by data providers and archive facility. | 2 | 0.2 | 8.7 | 15000 |  | 0.4 | 52200
| Task 5: Develop User Guide for Metadata | 3 | 0.25 | 8.7 | 15000 |  | 0.75 | 97875
Requirement: Discovery: Develop and Maintain Catalog and Search Capability
Milestone 1: Convene a Catalog Architecture Working Group
Milestone 2: Determine Architecture
| Task 1: Design Catalog Architecture | 6 | 0.5 | 8 | 15000 |  | 3 | 360000
| Task 2: Determine single vs. multiple catalogs | 2 | 0.4 | 3.7 | 15000 |  | 0.8 | 44400
Milestone 3: Determine Search/Browse Capabilities Needed
| Task 1: Determine the level of search/browse needed. | 2 | 0.4 | 4.4 | 15000 |  | 0.8 | 52800
| Task 2: Get User Feedback on Search/Browse Needs | 2 | 0.4 | 4.4 | 15000 |  | 0.8 | 52800
| Task 3: Choose, schedule search capabilities to be implemented | 2 | 0.4 | 5 | 15000 |  | 0.8 | 60000
Milestone 4: Determine Metadata Loading and Update Procedures
| Task 1: Write Catalog Management Plan | 4 | 0.5 | 8 | 15000 |  | 2 | 240000
Milestone 5: Plan Catalog Security (Cross-discipline with all DMAC)
| Task 1: Determine Catalog Security needs with DMAC | 3 | 0.4 | 3.6 | 15000 |  | 1.2 | 64800
| Task 2: Determine Catalog Access needs | 3 | 0.25 | 4.4 | 15000 |  | 0.75 | 49500
| Task 3: Write Catalog Security Plan | 3 | 0.5 | 3 | 15000 |  | 1.5 | 67500
Milestone 6: Build Initial Capability (pilots are needed, tbd)
| Task 1: Build catalog | 6 | 0.5 | 12 | 15000 |  | 3 | 540000
| Task 2: Populate Catalog | 10 | 0.1 | 12 | 15000 |  | 1 | 180000
| Task 3: Build initial User interface (may be web portal) | 4 | 0.25 | 9 | 15000 |  | 1 | 135000
Milestone 7: Transition to pre-operational and operational systems
| Task 1: Transition to Pre-Operational | 2 | 0.2 | 4.4 | 15000 |  | 0.4 | 26400
| Task 2: Transition to Operational | 4 | 0.25 | 4.4 | 15000 |  | 1 | 66000
Requirement: Discovery: Design Discovery Portal
Milestone 1: Initial portal design
| Task 1: Design overall Architecture | 4 | 0.5 | 4.4 | 15000 |  | 2 | 132000
| Task 2: Search Content and Scope | 4 | 0.5 | 5.1 | 15000 |  | 2 | 153000
| Task 3: Incorporate user feedback | 4 | 0.5 | 5.8 | 15000 |  | 2 | 174000
| Task 4: Determine access given to public search engines, e.g. Google | 4 | 0.5 | 5.8 | 15000 |  | 2 | 174000
| Task 5: Pilot Data Portal - NOAA NCDDC | 4 | 0.25 | 6.5 | 15000 |  | 1 | 97500
| Task 6: Pre-operational Data Portal | 2 | 0.25 | 7.3 | 15000 |  | 0.5 | 54750
| Task 7: Operational Data Portal | 2 | 0.1 | 18.1 | 15000 |  | 0.2 | 54300
Requirement: Discovery: Study Alternate Discovery Approaches
Milestone 1: Study an Implementation language neutral approach.
| Task 1. Study, report alternatives like web service. | 4 | 0.25 | 8 | 15000 |  | 1 | 120000
Milestone 2: Study feasibility of using semantic web.
| Task 1. Convene a working group to study semantic web feasibility | 4 | 0.25 | 13 | 15000 |  | 1 | 195000
Milestone 3: R&D or Pilot study of alternate approaches in DMAC |  |  |  |  | 15000 |  | 0 | 0
| Task 1: R&D or Pilot study of alternate approaches | 4 | 0.25 | 8 | 15000 |  | 1 | 120000
Requirement: Determine Specifications for Data Location Service
Milestone 1: Determine Specifications for Data Location Service
| Task 1: Determine specification for finding path to the requested data. | 3 | 0.4 | 4.4 | 15000 |  | 1.2 | 79200
| Task 2: Determine specification for finding individual granules of requested data . | 3 | 0.4 | 4.4 | 15000 |  | 1.2 | 79200
Total for Metadata/Data Discovery | [6 empty] | 4972725
Item | Task | Staffing | % time | Duration (m) | Rate | Unit Cost | Units | Cost
DATA ARCHIVE AND ACCESS
Requirement: Current archive and access assessment
Milestone 1: Publish a current archive and access assessment report covering all U.S. centers holding IOOS-relevant datasets.
| Task 1: Convene a working group with archive and scientific representatives from all IOOS data disciplines. | 6 | 0.15 | 6 | 15000 |  | 0.9 | 81000
| Task 2: Establish the set of dataset descriptive parameters. | 4 | 0.2 | 9 | 15000 |  | 0.8 | 108000
| Task 3: Evaluate the current status and publish the findings. | 4 | 0.1 | 12 | 15000 |  | 0.4 | 72000
Requirement: Determine dataset priorities for all IOOS data disciplines
Milestone 1: Develop criteria for ranking datasets. Establish priority lists for each data discipline.
| Task 1: Form a broad experienced expert team from all IOOS data disciplines. | 6 | 0.1 | 6 | 15000 |  | 0.6 | 54000
| Task 2: Convene a working group. | 6 | 0.1 | 12 | 15000 |  | 0.6 | 108000
Milestone 2: Map the unfulfilled IOOS archiving needs onto participating centers in the Archive System.
| Task 1: Working group to map all IOOS critical data on Archive System | 4 | 0.2 | 6 | 15000 |  | 0.8 | 72000
Milestone 3: List the products that are unavailable, but could be developed.
| Task 1: Form a ranked list of datasets that could be developed. | 4 | 0.05 | 6 | 15000 |  | 0.2 | 18000
| Task 2: Assess archive centers' infrastructure capabilities for absorbing work. | 6 | 0.1 | 6 | 15000 |  | 0.6 | 54000
Requirement: Determine IOOS dataset classification
Milestone 1: Assign dataset classification to all IOOS datasets.
| Task 1: Convene a working group | 4 | 0.1 | 12 | 15000 |  | 0.4 | 72000
| Task 2: Establish a process to categorize all IOOS datasets. | 4 | 0.1 | 12 | 15000 |  | 0.4 | 72000
| Task 3: Assure irreplaceable data security | 4 | 0.25 | 12 | 15000 |  | 1 | 180000
Requirement: Recruit centers for the IOOS Archive System and form partnerships |  |  |  |  | 15000 |  | 0 | 0
Milestone 1: Establish a set of guidelines for IOOS Archive System centers |  |  |  |  | 15000 |  | 0 | 0
| Task 1: Bring together the relevant IOOS governance and data policies into a set of guidelines. | 3 | 0.25 | 6 | 15000 |  | 0.75 | 67500
Milestone 2: Build international partnerships
| Task 1: Maintain a list of international centers and programs that could be collaborating partners for IOOS. | 1 | 0.05 | 39 | 15000 |  | 0.05 | 29250
| Task 2: Identify contacts and promote cross program partnerships and support. | 2 | 0.05 | 39 | 15000 |  | 0.1 | 58500
Milestone 3: Evaluate and plan for commercial overlaps
| Task 1: Survey the commercial data business and identify overlaps with the IOOS goals. Identify leverage areas. | 4 | 0.05 | 39 | 15000 |  | 0.2 | 117000
Requirement: Develop archive critical metadata |  |  |  |  | 15000 |  | 0 | 0
Milestone 1: Develop a comprehensive list of archive critical metadata and organize a planfor a system-wide metadata standard. |  |  |  |  | 15000 |  | 0 | 0
| Task 1: Convene a working group for data archiving and metadata development to prepare the list | 6 | 0.1 | 6 | 15000 |  | 0.6 | 54000
| Task 2: Interact with the DMAC Metadata and Discovery Data development team to ensure archive needs are accommodated. | 2 | 0.2 | 27 | 15000 |  | 0.4 | 162000
Milestone 2: Integrate these aspects of metadata with those necessary for machine access. |  |  |  | 21 | 15000 |  | 0 | 0
Requirement: Define IOOS archive and access data policy
Milestone 1: Develop a draft IOOS data policy
| Task 1: Form a committee for data archiving and IOOS management to draft the policy | 4 | 0.2 | 12 | 15000 |  | 0.8 | 144000
Milestone 2: Receive community comment on the draft policy |  |  |  |  | 15000 |  | 0 | 0
| Task 1: Circulate the policy. | 2 | 0.1 | 12 | 15000 |  | 0.2 | 36000
Milestone 3: Create a final draft.
| Task 1: Resolve problems raised by the IOOS user community and ensure the data policies can be applied satisfactorily. | 3 | 0.2 | 12 | 15000 |  | 0.6 | 108000
Requirement: Establish IOOS data stream developers guidelines
Milestone 1: Publish a guideline document, that is updated as progress and evolution in the DMAC takes place
| Task 1: Publish IOOS Data Stream Developers' Guide. | 2 | 0.25 | 12 | 15000 |  | 0.5 | 90000
Requirement: Develop Archive System data discovery interfaces
Milestone 1: Define the human data discovery interface
| Task 1: Work with the metadata and discovery data component. | 2 | 0.2 | 39 | 15000 |  | 0.4 | 234000
| Task 2: Dynamically harvest metadata and build IOOS metadata databases for discoverys | 2 | 0.4 | 33 | 15000 |  | 0.8 | 396000
| Task 3: Pilot - Other metadata and discovery tasks. | 4 | 0.15 | 33 | 15000 |  | 0.6 | 297000
Milestone 2: Define the machine data discovery interface
| Task 1: Specify machine interfaces with DMAC teams | 2 | 0.2 | 15 | 15000 |  | 0.4 | 90000
Requirement: Receive and provide more data in real time
Milestone 1: Put in place pilot projects and pre-operational real-time data systems based on DMAC data transport mechanism and existing data delivery infrastructure.
| Task 1: Select several real-time data streams that are most important | 4 | 0.05 | 12 | 15000 |  | 0.2 | 36000
| Task 2: Design pilot projects within the Archive System that include the components for real-time data receipt and immediate public access. | 2 | 0.2 | 12 | 15000 |  | 0.4 | 72000
| Task 3: Implement components within the projects (e.g. data receipt and delivery, etc.) | 6 | 0.25 | 12 | 15000 |  | 1.5 | 270000
| Task 4: Pilot project to serve near real-time GTSPP data. | 4 | 0.25 | 12 | 15000 |  | 1 | 180000
Requirement: Establish a protocol to report and resolve data and data flow problems
Milestone 1: Establish a protocol for reporting problems.
| Task 1: Determine the best way to report data stream or product problems so that users can be quickly informed. | 2 | 0.2 | 12 | 15000 |  | 0.4 | 72000
Milestone 2: Establish a protocol for documenting the resolution of the problem.
| Task 1: Follow the efforts in Milestone 1 | 2 | 0.25 | 12 | 15000 |  | 0.5 | 90000
Milestone 3: Determine effective ways to solve chronic problems
| Task 1: Investigate if IOOS management through Facilities Management Outreach can assist in resolving chronic problems. | 2 | 0.1 | 12 | 15000 |  | 0.2 | 36000
Milestone 4: Implement a DMAC system for data problems |  | 4 | 0.5 | 6 | 15000 |  | 2 | 180000
Requirement: Broaden the base for user services |  |  |  |  | 15000 |  | 0 | 0
Milestone 1: Define the most needed services that are missing from the IOOS Archive System.
| Task 1: Form a group of experts with strong representation from the User Outreach component to define the critical data service elements missing from the Archive System. | 4 | 0.1 | 18 | 15000 |  | 0.4 | 108000
Milestone 2: Determine how archive component can meet user needs.
| Task 1: Meet with Archive System representative to determine a strategy. | 2 | 0.1 | 18 | 15000 |  | 0.2 | 54000
Milestone 3: Implement new services
| Task 1: Pilot projects with users to develop needed data products, services. | 6 | 0.2 | 16 | 15000 |  | 1.2 | 288000
Requirement. Verify data security requirements for irreplacable datasets
Milestone 1: Run live tests to verify security of irreplacable IOOS data
| Task 1: Pilot project to randomly check between archive copies. | 4 | 0.2 | 12 | 15000 |  | 0.8 | 144000
| Task 2: Pilot. Execute data and inventory checks, recovery tests. | 4 | 0.2 | 12 | 15000 |  | 0.8 | 144000
Milestone 2: Propose regular verification procedure. |  | 2 | 0.1 | 12 | 15000 |  | 0.2 | 36000
Requirement. Metrics. Improve efficiency, maintainability of archive ingest, maintenance
Milestone 1: Seclect metrics required for both incoming and outgoing data.
| Task 1: DMAC Working group with representatives to determine metrics. | 4 | 0.2 | 12 | 15000 |  | 0.8 | 144000
Milestone 2: Compile a test annual report for DMAC Archive System
| Task 1: Pilot. Collect annual metrics from Archive System and refine. | 3 | 0.1 | 12 | 15000 |  | 0.3 | 54000
Milestone 3. Include Metric Requirements in Data Stream Developers' Guidelines.
Requirement. Procedure to resolve data retention issues.
Milestone 1: Consensus resolving data retention issues
| Task 1: Expert Team to draft data retention procedures. | 4 | 0.05 | 15 | 15000 |  | 0.2 | 45000
| Task 2: Develop schedule for removal of datasets identified for removal. | 2 | 0.1 | 15 | 15000 |  | 0.2 | 45000
Requirement. Security task does not appear in Archive & Access plan
Milestone 1: Plan Archive & Access Security
| Task 1: Determine Archive & Access Security wrt DMAC & Data Suppliers | 4 | 0.2 | 5 | 15000 |  | 0.8 | 60000
| Task 2: Determine Archive & Access Access needs. | 4 | 0.2 | 5 | 15000 |  | 0.8 | 60000
Total forArchive & Access | [6 empty] | 4892250

## Infrastructure
Item | Staffing | % time | Duration (m) | Rate | Unit Cost | Units | Cost
Communications
Communcations hardware |  |  |  |  | 100000 | 50 | 5000000
Installation/integration |  | 1 | 0.5 | 12000 | 6000 | 50 | 300000
Lease of communications services | [6 empty] | 2000000
Servers at centers
Hardware |  |  |  |  | 200000 | 50 | 10000000
Software |  |  |  |  | 40000 | 50 | 2000000
Total Infrastructure | [6 empty] | 19300000
Assumptions: Five regions, ten centers (servers) per region Communications cost TBD; annual estimate shown.