## Financial Statement
FINANCIAL STATEMENT
TCS Programme No. | 1765 |  | University ref. no |  | JP99 |  | Date |  |  | 1995-08-27
Company | ABC Company Ltd |  | Associates | Awarded | 2 |  | Grant | Period |  | 01/05/94 to 30/04/97
University | Queens University |  |  | In Post | 2 |  |  | Value |  | 91000
Department | Department of Philology |  |  | Former | 0 |  |  | Contribution |  | 70%
|  | BUDGET |  | EXPENDITURE |  |  | FORECAST |  |  | PROJECTED TOTALS
Expenditure Headings |  |  |  | To previous | Since previous | To date | Committed | Additional |  | Total | (Over)/
|  |  |  | statement | statement | [5 empty] | Under
|  | A |  | B | C | B+C=D | E | F |  | D+E+F=G | A-G=H
|  | £ |  | £ | £ | £ | £ | £ |  | £ | £
1. Associate salaries |  | 74000 |  | 18270 | 5710 | 23980 | 47958 | 3062 |  | 75000 | -1000
2. Academic & Secretarial Support |  | 34000 |  | 13200 | 2833 | 16033 | 17967 | 0 |  | 34000 | 0
3. Associate Development |  | 6000 |  | 1251 | 521 | 1772 | 2500 | 1728 |  | 6000 | 0
4. Travel & subsistence |  | 4000 |  | 833 | 1290 | 2123 | 425 | 452 |  | 3000 | 1000
5. Equipment, consumables & other |  | 12000 |  | 2670 | 40 | 2710 | 1200 | 8090 |  | 12000 | 0
6. Total |  | 130000 |  | 36224 | 10394 | 46618 | 70050 | 13332 |  | 130000 | 0
Income Headings
7. Grant |  | 91000 | [7 empty] | 90300 | 700
8. Company contribution |  | 39000 | [7 empty] | 39700 | -700
9. Total |  | 130000 | [7 empty] | 130000 | 0
Effort measured in associate months |  | 48 |  | 12 | 4 | 16 | 32 | 0 |  | 48 | 0
Comments / Notes | [6 empty] | Invoices outstanding |  | Inv. no. | Issue date | Amount
[7 empty] | 01/05/95 to 31/07/95 |  | 12045 | 1995-07-31 | 11527.57

## Second page
TCS Programme No. | 1765 | [10 empty] | Date | 1995-08-27
Company | ABC Company Ltd
University | Queens University
Department | Department of Philology
Available
Associate Development |  | 6000
Travel & Subsistence |  | 4000
Equipment, consumables & other |  | 12000
22000
Expenditure Headings |  | TCA1 |  | TCA 2 |  | Academic 1 |  | Academic 2 |  | Total |  | (Over)/
|  | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Under
Car mileage & public transport |  | 300 | 222 | 300 | 25 | 300 | 0 | 300 | 0 | 1200 | 247 | 953
Travel etc. to TCD courses |  | 800 | 694 | 800 | 0 | 0 | 0 | 0 | 0 | 1600 | 694 | 906
UK courses, visits, conferences* |  | 1000 | 727 | 1000 | 0 | 0 | 0 | 0 | 0 | 2000 | 727 | 1273
Foreign courses, visits, conferences* |  | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000
Certificate of management practice |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 2000 | 1000 | 1000
SoTCA seminar* |  | 400 | 357 | 400 | 0 | 0 | 0 | 0 | 0 | 800 | 357 | 443
TCS seminar* |  | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 800
European affairs* |  | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 1600
Postgraduate course fees |  | 1000 | 870 | 1000 | 0 | 0 | 0 | 0 | 0 | 2000 | 870 | 1130
Equipment/ miscellaneous |  | 2500 | 2630 | 2500 | 0 | 1000 | 80 | 1000 | 0 | 7000 | 2710 | 4290
Totals |  | 9700 | 6500 | 9700 | 25 | 1300 | 80 | 1300 | 0 | 22000 | 6605 | 15395
Comments/Notes
1. All items marked * include registration, fees, travel, subsistence etc.

## Notes
The Financial Statement Guidance notes
What is it for?
Its primary purpose is as a decision making tool to provide the Local Management Committee (LMC) with details
relating to the current financial state of the programme and a forecast outturn. This should allow the LMC to
ensure that expenditure approved is within budget or, if not, to ensure that the company is aware that additional
funds may be required. This format is the approved format for all programmes which started on or after 01/04/95.
The proforma is available from TCD at Faringdon as a form or as an Excel spreadsheet. There is a second
sheet which is not compulsory but may be used to provide further analysis of some of the headings used in the
Financial Statement.
When is it required?
The financial statement should be produced at approximately quarterly intervals to suit the LMC meetings.
Who needs it?
The LMC will need it and a copy should be sent to TCD at Faringdon attached to the minutes of the relevant
meeting.
Who prepares it?
This will vary from programme to programme so the responsibility for preparation and submission is at the
discretion of the LMC.
How is it prepared?
TCS programme No. |  | The unique four digit number quoted in the offer letter.
University ref. no. |  | This number will have been created by the university for their own
internal purposes.
Date |  | The date the document is prepared for the LMC meeting.
Company |  | The name of the industrial partner in the programme.
University |  | The name of the academic institution involved in the programme or, if there
is more than one, the lead institution.
Department |  | The name of the department within the academic institution involved with the
programme.
Associates | Awarded | The maximum number of associates either working on or expected to be
working on the programme e.g. 2 for a 121 programme or 4 for a 242 programme.
| In Post | The number of associates currently employed.
| Former | The number of associates who have left the programme.
Grant | Period | The start date and the anticipated end date of the programme.
| Value | The total grant available from the Directorate as set out in the offer letter in paragraph 1.
| Contribution | The percentage of the overall cost of the programme represented by the Directorate's
grant as set out in schedule 1, column 3 of the offer letter.
Expenditure Headings
BUDGET |  | This is as per the Offer Letter schedule 1 column 1.
EXPENDITURE
To previous statement |  | This will be the 'EXPENDITURE To date' from the prior Financial statement or, if
this is the first such statement then it will be blank.
Since previous statement |  | This should reflect the resources used since the last meeting
To date |  | This is the sum of 'To previous statement' and 'Since previous statement'. It reflects
all the resources used to date and will be carried forward to 'To previous statement'
when the next Financial Statement is prepared.
FORECAST
Committed |  | This shows those resources which have been committed but not yet spent (e.g. the
remaining salary of the first associate in a 121 programme).
Additional |  | The best estimate of other resources which it is anticipated will be used but to which
no commitment has yet been made.
PROJECTED TOTALS
Total |  | This is the sum of 'To date', 'Committed' and 'Additional'.
(Over)/Under |  | This shows projected over or under spend of projected total expenditure against
the BUDGET. An overspend will be bracketed and an underspend will not. In
respect of moving funds between headings your attention is drawn to paragraph 4
of the offer letter.
Effort measured in |  | This is a useful guide to check the rate of expenditure and is an indication of the
Associate months |  | progress of the programme.
Income Headings
Grant |  | The budget figures should be as per the offer letter Schedule 1 column 2.
Company contribution |  | The budget figures should be as per the offer letter Schedule 1 column 3.
PROJECTED TOTALS |  | Income should always offset projected expenditure exactly.
Comments/Notes |  | These may be used at the discretion of the LMC or the person preparing
the Financial Statement.
Invoices outstanding |  | This may be used at the discretion of the LMC or the person preparing
the Financial Statement to reflect unpaid invoices issued by the University.

## Blank Financial Statement
FINANCIAL STATEMENT
TCS Programme No. |  | University ref. no |  |  |  | Date
Company |  | Associates | Awarded |  |  | Grant | Period
University |  |  | In Post |  |  |  | Value
Department |  |  | Former |  |  |  | Contribution
| BUDGET |  | EXPENDITURE |  |  | FORECAST |  |  | PROJECTED TOTALS
Expenditure Headings |  |  | To previous | Since previous | To date | Committed | Additional |  | Total | (Over)/
|  |  | statement | statement | [5 empty] | Under
| A |  | B | C | B+C=D | E | F |  | D+E+F=G | A-G=H
| £ |  | £ | £ | £ | £ | £ |  | £ | £
1. Associate salaries
2. Academic & Secretarial Support
3. Associate Development
4. Travel & subsistence
5. Equipment, consumables & other
6. Total
Income Headings
7. Grant
8. Company contribution
9. Total
Effort measured in associate months
Comments / Notes | [5 empty] | Invoices outstanding |  | Inv. no. | Issue date | Amount

## Blank Second Page
TCS Programme No. | [9 empty] | Date
Company
University
Department
Available:
Associate Development
Travel & Subsistence
Equipment, consumables & other
Expenditure Headings | TCA1 |  | TCA 2 |  | Academic 1 |  | Academic 2 |  | Total |  | (Over)/
| Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Under
Car mileage & public transport
Travel etc. to TCD courses
UK courses, visits, conferences
Foreign courses, visits, conferences
Certificate of management practice
SoTCA seminar
TCS seminar
European affairs
Postgraduate course fees
Equipment/ miscellaneous
Totals
Comments/Notes