## Timeline Information
Task # | Task Name | Devices | Duration | Hours | Start Date | End Date | Dependency | Staff | All Staff | Hrs/ws
| Network Migrations |  | Days | Labor |  |  |  | 1 week
| Juneau - DMV - Field office | 10 | 4 | 51.75 | 1999-10-15 | 1999-10-18 | Pending Netopia Hub & wiring | 1.2937 | 9.7063
| Soldotna - DMV | 10 | 4 | 51.75 | 1999-10-15 | 1999-10-18 | Troubleshooting with GCI | 1.2937 | 9.7063
| Bethel - PD | 10 | 6 | 51.75 | 1999-10-01 | 1999-10-06 | Planning/Wiring/Servers | 1.2937 | 9.7063
| Anchorage - Move DGS users to R&B server in BOA | 8 | 1 | 41.4 | 1999-10-10 | 1999-10-13 | Pending R&B move | 1.035 | 9.965
| Juneau - R&B expansion & move ? | 40 | 5 | 207 | 1999-11-15 | 1999-11-19 | Couple of sections to Annex | 5.175 | 5.825
| Juneau - R&B Wiring ? | 120 | 6 | 207 | 1999-11-15 | 1999-11-20 | Switched Ethernet & Nics | 5.175 | 5.825
| Anchorage - ALP | 36 | 5 | 186.3 | 1999-11-15 | 1999-11-19 | Planning/Wiring/Servers | 4.6575 | 6.3425
| Homer - DMV | 2 | 3 | 10.35 | 1999-11-10 | 1999-11-12 | Pending Netopia, cablemodem or dialup
| Haines - DMV | 3 | 1 | 15.525 |  |  | Pending Netopia, cablemodem or dialup
| Valdez - DMV | 4 | 1 | 20.7 |  |  | Pending Netopia, cablemodem or dialup
| Delta Junction - DMV | 2 | 1 | 10.35 |  |  | Pending Netopia, cablemodem or dialup
| Bethel - DMV | 2 | 1 | 10.35 |  |  | Pending Netopia, cablemodem or dialup
| Anchorage - AOGCC (rebuild of O/S 2 net) | 22 | 1 | 113.85 |  |  | Pending Wiring | 2.8462 | 8.1538
| Juneau - ITG (consolidate to site server) | 75 | 1 | 388.125 |  |  | Pending Network Changes | 9.7031 | 1.2969
| Anchorage - ITG (consolidate to DMV server) | 50 | 4 | 258.75
Software Installs
| Fat Client software (10) | 320 | 1 | 552 |  |  | OMB, Finance & others | 13.8 | -2.8 | 1.5 | Ave. Hours per ws install
Database, emulation & connectivity tools
| Hardware Installs | [6 empty] | 2 weeks ea
| New Workstations | 124 | 73 | 641.7 | 1999-06-20 | 1999-08-31 | By plan | 8.0213 | 2.9787 | 4.5 | Ave. Hours per ws install
| New Workstations | 185 | 50 | 957.375 | 1999-09-13 | 1999-11-01 | By plan | 11.9672 | -0.96719
| New Workstations | 50 | 182 | 258.75 | 2000-01-01 | 2000-06-30 | Projected | 3.2344 | 7.7656
| Lifecycle replacement Servers - ITG Telcom (Fbx & Anch) | 2 | 8 | 70 | 1999-10-04 | 1999-10-11 | By plan | 2 | 9
Projects
| Netscape 4.51 install | 853 | 69 | 490.475 | 1999-09-01 | 1999-11-08 | 4 weeks | 3.0655 | 7.9345
| MS Office '97 install | 853 | 69 | 490.475 | 1999-09-01 | 1999-11-08 | 4 weeks | 3.0655 | 7.9345
| Y2K Windows O/S patch | 853 | 252 | 490.475 | 1999-03-09 | 1999-11-15 | 4 weeks | 3.0655 | 7.9345 | 0.5 | Ave Hours per ws
| Y2K MS Office patch | 853 | 252 | 490.475 | 1999-03-09 | 1999-11-15 | 4 weeks | 3.0655 | 7.9345
| Y2K desktop test | 853 | 252 | 490.475 | 1999-03-09 | 1999-11-15 | 4 weeks | 3.0655 | 7.9345
| Upgrade Servers to Innoculan 4.0 | 30 | 215 | 17.25 | 1999-03-09 | 1999-10-09 | 9 weeks | 2 | 9
| Upgrade Servers to Managewise 2.6 | 30 | 215 | 17.25 | 1999-03-09 | 1999-10-09 | 1 week | 2 | 9
| Config Central propagation software to server network | 40 | 32 | 69 | 1999-07-15 | 1999-08-15 | 4 weeks | 2 | 9
| Restructure of DOA NDS Network | 50 | 214 | 258.75 | 1999-11-15 | 2000-06-15 | 7 mos. | 2 | 9
| Migrate Intranet web server to DOA tree | 1 | 8 | 70 | 1999-10-04 | 1999-10-11
Maintenance
| Devices@ 1/2 hr. /node/week | 1245 |  | 622.5 |  |  |  | 15.5625 | -4.5625

## Migrations Finished
Task # | Task Name | Devices | Duration | Hours | Start Date | End Date | Actual Staff | Projected Staff | Available Staff | Hrs/ws | Why
| Network Migrations |  | Days | Labor |  |  | Project Staff based on 1 week
June '97 - Pre DOAIT - Must be redone
| APOC - Anch | 12 |  | 62.1 |  |  | 3 |  |  | 4.5 | Ave. Hours per ws install - Hardware
| PD - Anch | 45 |  | 232.875 |  |  | 4 |  |  | 1.5 | Ave. Hours per ws install - Software
| OPA - Anchorage | 45 |  | 232.875 | 342 | Start | 4 |  |  | 0.5 | Ave. Hours per ws install - Fat Client Software
| DMV - Juno | 30 |  | 155.25 | 165 | Stay on net | 4
| DMV - Anch HQ | 30 |  | 155.25 |  |  | 4
| DMV - Anch AFO | 30 |  | 155.25 | 1108 | Current | 4
| ITG - Anch | 50 |  | 258.75 |  |  | 3
| ITG - Juno | 75 |  | 388.125 |  |  | 3
| ITG - Fbx | 25 |  | 129.375 |  |  | 3
DOAIT Admin Network
| Risk Management | 10 | 13 | 51.75 | 1998-02-17 | 1998-03-01 | 3 | 1.2937 | 1.7063
| Tax Appeals | 5 | 5 | 25.875 | 1998-02-25 | 1998-03-01 | 1 | 0.64687 | 2.3531
| APDI Lab - Juneau | 15 | 7 | 77.625 | 1998-02-23 | 1998-03-01 | 5 | 1.9406 | 1.0594
| Labor Relations | 10 | 4 | 51.75 | 1998-03-26 | 1998-03-29 | 5 | 1.2937 | 1.7063
| DAS | 41 | 46 | 212.175 | 1998-04-01 | 1998-05-16 | 5 | 5.3044 | -2.3044
| General Services - Juneau | 21 | 16 | 108.675 | 1998-05-16 | 1998-05-31 | 5 | 2.7169 | 0.28313
| General Services - Anchorage | 16 | 4 | 82.8 | 1998-05-28 | 1998-05-31 | 2 | 2.07 | 0.93
| ITG - Anchorage | 50 | 10 | 258.75 | 1998-08-12 | 1998-08-21 | 4 | 6.4688 | 5.5312
| DMV - Anchorage HQ | 42 | 10 | 217.35 | 1998-08-12 | 1998-08-21 | 4 | 5.4337 | 6.5663
| Personnel - Juneau | 60 | 15 | 310.5 | 1998-09-01 | 1998-09-15 | 5 | 7.7625 | 4.2375
| Finance - Juneau | 70 | 40 | 362.25 | 1998-10-12 | 1998-11-20 | 5 | 9.0563 | 2.9438
| PD - Fairbanks | 21 | 35 | 108.675 | 1998-12-11 | 1999-01-14 | 2 | 2.7169 | 9.2831
| DMV - Fairbanks | 15 | 35 | 77.625 | 1998-12-11 | 1999-01-14 | 4 | 1.9406 | 9.0594
| OPA - Fairbanks | 14 | 35 | 72.45 | 1998-12-11 | 1999-01-14 | 4 | 1.8113 | 9.1888
| R&B - Anchorage | 15 | 7 | 77.625 | 1998-12-18 | 1998-12-24 | 1 | 1.9406 | 9.0594
| OPA - Anchorage | 45 | 56 | 232.875 | 1999-01-08 | 1999-03-04 | 4 | 5.8219 | 7
| Senior Services - Juneau | 13 | 8 | 67.275 | 1999-01-08 | 1999-01-15 | 3 | 1.6819 | 8
| Pioneers homes - Juneau | 17 | 8 | 87.975 | 1999-01-08 | 1999-01-15 | 2 | 2.1994 | 9
| Y2K Office - Juneau | 5 | 6 | 25.875 | 1999-01-10 | 1999-01-15 | 1 | 0.64687 | 10
| PD - Juneau | 9 | 7 | 46.575 | 1999-02-04 | 1999-02-10 | 1 | 1.1644 | 10
| OPA - Juneau | 5 | 7 | 25.875 | 1999-02-04 | 1999-02-10 | 2 | 0.64687 | 9
| DMV - Palmer | 9 | 72 | 46.575 | 1998-12-15 | 1999-02-24 | 4 | 1.1644 | 7
| PD - Palmer | 10 | 100 | 51.75 | 1998-12-15 | 1999-03-24 | 4 | 1.2937 | 7
| Anchorage - Personnel Move | 23 | 5 | 119.025 | 1999-02-23 | 1999-02-27 | 1 | 2.9756 | 10
| Juneau - ALP HQ | 24 | 5 | 124.2 | 1999-03-08 | 1999-03-12 | 3 | 3.105 | 8
| Ketchikan - DMV, PD & ALP | 30 | 6 | 155.25 | 1999-03-19 | 1999-03-24 | 2 | 3.8813 | 9
| Anchorage - Senior Svcs. | 57 | 8 | 294.975 | 1999-04-05 | 1999-04-12 | 7 | 7.3744 | 3.6256
| Anchorage - DMV - AFO | 55 | 3 | 284.625 | 1999-04-23 | 1999-04-25 | 6 | 7.1156 | 3.8844
| Sitka - ALP, DMV & PD | 30 | 6 | 155.25 | 1999-04-30 | 1999-05-05 | 3 | 3.8813 | 7.1188
| Anchorage - DMV - 5th Ave Downtown | 10 | 3 | 51.75 | 1999-05-19 | 1999-05-21 | 2 | 1.2937 | 9.7063
| Fairbanks - ALP | 30 | 4 | 155.25 | 1999-05-21 | 1999-05-24 | 4 | 3.8813 | 7.1188
| Palmer - ALP | 22 | 4 | 113.85 | 1999-05-28 | 1999-05-31 | 2 | 2.8462 | 8.1538
| Anchorage - R&B | 14 | 4 | 72.45 | 1999-06-25 | 1999-06-28 | 2 | 1.8113 | 9.1888
| Anchorage - DMV - Eagle River | 10 | 3 | 51.75 | 1999-06-13 | 1999-06-15 | 2 | 1.2937 | 9.7063
| Kenai - PD | 10 | 4 | 51.75 | 1999-08-20 | 1999-08-23 | 2 | 1.2937 | 9.7063
| Anchorage - R&B move to 10th fl BOA | 15 | 4 | 77.625 | 1999-09-30 | 1999-10-04 | 1 | 1.9406 | 9.0594
| Juneau - R&B | 95 | 7 | 491.625 | 1999-09-28 | 1999-10-04 | 9 | 12.2906 | -1.2906
| Hardware Installs | [6 empty] | 2 weeks ea
| New Workstations | 300 | 216 | 1552.5 | 1998-07-15 | 1999-02-15
| Build of test network in Juneau | 15 | 17 | 77.625 | 1999-08-15 | 1999-08-31
| New Workstations | 124 | 73 | 641.7 | 1999-06-20 | 1999-08-31 | By plan | 8.0213 | 2.9787 | 4.5 | Ave. Hours per ws install
Software Installs
| Fat Client Installs (18x70) | 1260 | 199 | 724.5 | 1998-08-01 | 1999-02-15
Projects
| Netscape Email | 850 | 76 | 1466.25 | 1998-05-01 | 1998-07-15
| Commerce Server Build | 2 | 32 | 80 | 1999-01-15 | 1999-02-15
| Y2K server patches & testing | 46 | 32 | 79.35 | 1998-12-15 | 1999-01-15
| Comtec | 8 | 3 | 41.4 | 1999-02-03 | 1999-02-05
| ITG TNG Project | 200 | 193 | 1035 | 1999-01-04 | 1999-07-15
| Anchorage - Nal/Zen Knoledge transfer | 15 | 5 | 240 | 1999-04-05 | 1999-04-09 | 1 week | 6 | 5
| NT desktops, consoles & servers | 35
| Upgrade Servers to DS 6 | 47 | 84 | 81.075 | 1999-03-09 | 1999-05-31 | 1 week | 2.0269 | 8.9731
| Calander Upgrades - concurrent with migrations | 853 | 288 | 0 | 1999-01-01 | 1999-10-15 | 4 weeks | 0 | 11
| NetG Netscape plugin - x days after available | 853 | 93 | 0 | 1999-05-15 | 1999-08-15 | 4 weeks | 0 | 11
| Commerce Server Build | 1 | 15 | 40 | 1999-08-01 | 1999-08-15
Network Failures
| DMV Anch AFO | 25 | 2 days | 80 | 1998-09-01 | 1998-09-05 | 2 |  |  |  | Token Beaconing
| ALP - Sitka | 17 | 6 hrs | 8 | 1998-11-19 | 1998-11-19 | 1 |  |  |  | Power failure
| DMV Anch AFO | 25 | 5 hrs | 64 | 1999-01-05 | 1999-01-08 | 2 |  |  |  | Routing
| OPA/PD Building Power failure | 120 | 2 days | 8 | 1999-02-09 | 1999-02-09 | 1 |  |  |  | Power failure
| OPA/PD Building Power failure | 120 | 2 days | 8 | 1999-02-12 | 1999-02-12 | 1 |  |  |  | Power failure
| ALP - HQ (juno) | 24 | 2 hrs | 32 | 1999-03-06 | 1999-03-07 | 2 |  |  |  | Routing
| Juneau Site Server | 280 | 1 hr | 24 | 1999-03-22 | 1999-03-22 | 3 |  |  |  | NIC buffers
| DIS-Juneau | 75 | 2 hrs | 2 | 1999-05-11 | 1999-05-11 | 1 |  |  |  | Disk Space
| R & B - Juneau | 85 | 4 hrs | 8 | 1999-07-12 | 1999-07-12 | 3 |  |  |  | Bad cable/port
| DMV Anch DI - Dowling | 20 | 2 days | 28 | 1999-07-13 | 1999-07-13 | 2 |  |  |  | Change to Pub Saf network
| ALP - Sitka | 17 | 2 days | 12 | 1999-07-24 | 1999-07-25 | 1 |  |  |  | Hard drive failure
| DMV - Juneau | 10 | 1 day | 1 | 1999-08-16 | 1999-08-16 | 1 |  |  |  | Public Safety contractor(Jeffus) snipped phone line

## TimelineWizardData (hidden)
H:\VISIO\SOLUTIONS\BUSINESS DIAGRAM\Project Timeline Wizard.exe