## Summery
Component DeviceName: Main Linac Areas 500 RF Waveguide Vacuum Mechanical
WBS # 1142252 |  | Quantity: | 1 |  | Unit Cost: |  |  |  | Sorted
Sums
Activity | Estimator | Lbr Code | ED&I | M&S | Lbr Code | Labor | Equipment |  | (Pgroup) | Detailed Activities
[Initials]
Design | [JRW] | [8 empty] | System & Conceptual design, reliability design, simulations, modeling,
Design Engr |  | ENGV | [7 empty] | planning, estimating, scheduling, reports, design reviews
Design |  | DESM
Design & Fab. Prototype | [JRW] | [8 empty] | Detailed design of prototype hardware, firmware/software, control panels and interface, rework,
|  | ENGV | [7 empty] | built-in diagnostics, parts procurement, fabrication, test, design reviews,
|  | DESM | [7 empty] | test reports, Design for Manufacture, reliability engineering
Manufg- Pre-Production | [JRW] | [8 empty] | Develop manufacturing plan, quality plan, place contracts for pre-production, design & develop jigs and
|  | ENGV | [7 empty] | testers, factory tests for pre-production, design reviews, reports.
DESM
Manufacturing - Production | [JRW] | [8 empty] | Place manufacturing contracts, deliver special jigs and testers, install QC procedures,
|  | ENGV | [7 empty] | coordinate/track production through completion.
DESM
Inventory & Storage | [JRW] | [8 empty] | Design storage areas, coordinate with Conventional Facilities and Crafts,
develop inventory system, staff operation.
Subtotals |  | Lbr Code | Cost |  | Lbr Code | Cost
|  | ENGV | 1705000 |  | MACH | 546238
|  | DESM | 958464 |  | PLCL | 1488918.2
|  |  |  | 47547710 | WELD | 882592
[5 empty] | ASMM | 829218
[5 empty] | ASMV | 4271976
[5 empty] | ASMP | 445756.5
Totals |  |  | 2663464 | 47547710 |  | 8464698.7
Special Handling Activities
Pre-Assembly & Test** | [CoordEngr] | [8 empty] | Assemble manufactured components into assemblies, such as rack assemblies, mounting klystrons to modulators,
building magnet and structure rafts etc. QC inspection, records, rework records etc. Return finished
assemblies to inventory. RAM teams need to coordinate on estimates to define treaty points and avoid overlaps.
Installation - Cable Plant** | [CoordEngr] | [8 empty] | Define cable plant requirements, design cables, coordinate cost estimates with Cable Shop for engineering,
fabrication and installation and QC costs for each subsystem. Cables will be installed by Contract (Davis Bacon Labor).
Cable Shop will be responsible for cost estimate of total Tray requirements.
Installation - Hardware** | [CoordEngr] | [8 empty] | Develop installation, QC and training plan, contract installation, procure equipment and materials,
supervise installation, design review, installation reports.
RAM teams need to coordinate on estimates to define treaty points and avoid overlaps.
Installation - Software** | [CoordCtrls] | [8 empty] | Develop installation, QC and training plans for firmware/software installation,
hire/train personnel, supervise installation, QC, reports. Controls Department
will install global system software but subsystems need to check out using the global system.
System Test & Integration** | [CoordEngE] | [8 empty] | Design & develop system test, QC and manpower/ training plans, procure equipment and materials hire/train personnel,
| [CoordEngM] | [8 empty] | integrate with neighbor systems, test through controls, develop supporting documentation for Operations and
Maintenance. perform integrated hardware/software tests of all features possible without beam in the Accelerator.
Subtotals |  | Lbr Code | Cost |  | Lbr Code | Cost
Totals
|  |  |  | Estimate Approved By: |  |  | [HXK] | [Initials]
Non-Recurring Work Areas** |  | ED&I | Lbr Code | M&S | Labor | Lbr Code | Equipment | Space | PGroup
Laboratory design & setup | Engr/Mgr | [8 empty] | Design laboratory, procure furniture and specialized / standard test equipment, coordinate with builders
and crafts, plan and fulfil staffing. Calculate floor space requirements for use by Conventional Facilities.
Note special definition of Equipment in Dictionary.
Subtotals |  | Lbr Code | Cost |  | Lbr Code | Cost
Totals
Factory design & setup | [CoordEngr] | [8 empty] | Design factory, procure special fabrication and test equipment, coordinate with builders and crafts, plan and
fulfil staffing, develop work methods and procedures, develop training plans. Calculate floor space requirements
for use by Conventional Facilities. Note special definition of Equipment in Dictionary.
Subtotals |  | Lbr Code | Cost |  | Lbr Code | Cost
Totals
Pre-Assembly & Test area | [CoordEngr] | [8 empty] | Design pre-assembly & test area, procure special test equipment, coordinate with builders and crafts,
plan and fulfil staffing, develop work methods and procedures, develop training plans.
Calculate floor space requirements for use by Conventional Facilities.
Subtotals |  | Lbr Code | Cost |  | Lbr Code | Cost
Totals
R&D** | [Mgr] | [8 empty] | Restricted to large cost items, such as klystrons or the solid state modulator.
[10 empty] | Note Dictionary definition. Consult with management on this item. | Regular test and lab equipment
Lab or field test equipment should be listed as M&S against the appropriate activity.
Subtotals |  | Lbr Code | Cost |  | Lbr Code | Cost
Totals
System Commissioning** | [Mgr] | [8 empty] | System Commissioning begins when all systems begin simultaneous turn-on to establish beam
in the Accelerator. Management will consult with RAM groups in making these estimates.
Subtotals |  | Lbr Code | Cost |  | Lbr Code | Cost
Totals
|  |  |  | Estimate Approved By: |  |  | [HXK] | [Initials]
**Special Handling Notes:
1. Installation - Hardware | K. Fant |  | All installations costs are rolled up to an Installation worksheet by area. Special handling by designated engineer.
2. Installation - Cable Plant | P. Rodriguez |  | Costs are estimated by engineering in consultation with cable shop (P. Rodriquez). Rolled up into above.
3. Installation- Software | R. Fuller |  | Includes database and special software. Engineer coordinates with Controls. Sums into Global Controls.
4. System Test and Integration | CoordEngrs | TBD | Responsible Engineer / Manager estimates costs and rolls up to a separate worksheet. Special handling by designated engineer.
5. R&D, System Commissiong | CoordEngr | TBD | Management coordinates these estimates with Area and Engineering/management.
6. Non-Recurring Work Areas | J. Weinberg |  | Responsible Engineer calculates costs and space needs. Costs go to special Manufacturing Facilities worksheet. Space goes to Conv. Fac.
| CoordEngrs | TBD

## ML WC293
NLC ENGINEERING ESTIMATE
PROJECT: NLC Single Mode Delay Line WC293 W/ Eyelets |  |  |  | DATE: 6/19/98
ENGINEER: J. Weinberg |  |  |  | REVISION:
[6 empty] | B&H | [7 empty] | ED&I
|  | MATERIAL | [5 empty] | LABOR
ITEM | MEAS | # UNITS | UNIT COST | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL
Delay Line flg.-flg. | [7 empty] | 0 |  | 0 |  |  |  | 0 |  | 0
WC293 (3 in. Dia) Cu | 10m | 1792 | 294 | 526848 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Cu end collar | ea | 3584 | 6 | 21504 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
S.St. eyelet | ea | 3584 | 8 | 28672 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Glow Discharge Cleaning |  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Tech labor for GDC |  |  |  | 0 | 4.5 hr/pc | 1792 | 4.5 | 8064 | 39 | 314496 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
ENGINEERING | [7 empty] | 0 |  | 0 |  |  |  | 4000 | 55 | 220000
DESIGN | [7 empty] | 0 |  | 0 |  |  |  | 2000 | 52 | 104000
MECHANICAL FAB |  |  |  |  | HR | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
QC |  |  |  |  | HR | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
PRECISION ASSEMBLY |  |  |  |  | HR | 3584 | 0.25 | 896 | 63 | 56448 |  |  |  | 0 |  | 0
PLATING & CLEANING WC293 |  |  |  |  | HR | 1792 | 0.25 | 448 | 109 | 48832 |  |  |  | 0 |  | 0
PLATING & CLEANING |  |  |  |  | HR | 8960 | 0.01 | 89.6 | 109 | 9766.4 |  |  |  | 0 |  | 0
TORCH BRAZING |  |  |  |  | HR | 3584 | 0.25 | 896 | 77 | 68992 |  |  |  | 0 |  | 0
MECHANICAL TECHS |  |  |  |  | HR | 1792 | 1 | 1792 | 39 | 69888 |  |  |  | 0 |  | 0
SUBTOTAL |  |  |  | 577024 | [5 empty] | 568422.4 | [5 empty] | 324000
TOTAL B&H |  |  |  | 1145446.4
TOTAL ED&I |  |  |  | 324000
PROJECT TOTAL |  |  |  | 1469446.4

## MLWC 475
NLC ENGINEERING ESTIMATE
PROJECT: NLC Single Mode Delay Line WC475 W/ Eyelets |  |  |  |  | Date 3/10/99
ENGINEER: J. Weinberg
[6 empty] | B&H | [7 empty] | ED&I
|  | MATERIAL | [5 empty] | LABOR
ITEM | MEAS | # UNITS | UNIT COST | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL
Delay Line flg.-flg. | [7 empty] | 0 |  | 0 |  |  |  | 0 |  | 0
WC475 (5 in. Dia) Cu | 14m | 10000 | 723 | 7230000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Cu end collar | ea | 20000 | 15 | 300000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
S.St. eyelet | ea | 20000 | 25 | 500000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
eyetet adaptors/blanks | ea | 5000 | 15 | 75000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
eyelet clamps | ea | 2500 | 75 | 187500
tin seals | ea | 25000 | 1 | 25000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Supports for delay line per meter | ea | 10000 | 10 | 100000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Pump Tee | ea | 6624 | 1750 | 11592000
75 l/s ion pumps | ea | 6624 | 2000 | 13248000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Glow Discharge Cleaning |  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Tech labor for GDC |  |  |  | 0 | 4.5 hr/pc | 10000 | 4.5 | 45000 | 39 | 1755000 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
ENGINEERING | [7 empty] | 0 |  | 0 |  |  |  | 15000 | 55 | 825000
DESIGN | [7 empty] | 0 |  | 0 |  |  |  | 5000 | 52 | 260000
MECHANICAL FAB |  |  |  |  | HR | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
QC |  |  |  |  | HR | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
PRECISION ASSEMBLY |  |  |  |  | HR | 20000 | 0.25 | 5000 | 63 | 315000 |  |  |  | 0 |  | 0
PLATING & CLEANING WC475 |  |  |  |  | HR | 10000 | 0.25 | 2500 | 109 | 272500 |  |  |  | 0 |  | 0
PLATING & CLEANING |  |  |  |  | HR | 40000 | 0.01 | 400 | 109 | 43600 |  |  |  | 0 |  | 0
TORCH BRAZING |  |  |  |  | HR | 20000 | 0.25 | 5000 | 77 | 385000 |  |  |  | 0 |  | 0
MECHANICAL TECHS |  |  |  |  | HR | 10000 | 1 | 10000 | 39 | 390000 |  |  |  | 0 |  | 0
SUBTOTAL |  |  |  | 33257500 | [5 empty] | 3161100 | [5 empty] | 1085000
TOTAL B&H |  |  |  | 36418600
TOTAL ED&I |  |  |  | 1085000
PROJECT TOTAL |  |  |  | 37503600
Includes the cost of ion pumps and processing of the delay line.

## ML Kly. Gal. Vac.
NLC ENGINEERING ESTIMATE
PROJECT: NLC Main Linac Klystron Gallery Waveguide Vacuum System |  |  |  | DATE: 6/15/98
ENGINEER: J. Weinberg |  |  |  | REVISION:
[6 empty] | B&H | [7 empty] | ED&I
|  | MATERIAL | [5 empty] | LABOR
ITEM | MEAS | # UNITS | UNIT COST | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL
[8 empty] | 0 |  | 0 |  |  |  | 0 |  | 0
1.5" cross w/ 2.75 conflat flngs. | ea | 1656 | 90 | 149040 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
gaskets | ea | 6624 | 0.5 | 3312 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
bolt sets | ea | 6624 | 3 | 19872 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Rt. angle valve w/ 2.75 flanges | ea | 1656 | 350 | 579600
Convectron gauge package | ea | 1035 | 400 | 414000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Waveguide valve | ea | 0 | 0 | 0
25 l/s ion pump | ea | 1584 | 1200 | 1900800 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Turbo roughing system | ea | 198 | 8000 | 1584000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Vacuum Bakeout |  |  |  | 0 | 4 hr/pc | 1656 | 4 | 6624 | 40 | 264960 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
ENGINEERING | [6 empty] | 0 | 0 |  | 0 |  |  |  | 6000 | 55 | 330000
DESIGN | [6 empty] | 0 | 0 |  | 0 |  |  |  | 2000 | 52 | 104000
MECHANICAL FAB |  |  |  |  | HR | 4718 | 1 | 4718 | 77 | 363286 |  |  |  | 0 |  | 0
QC |  |  |  |  | HR | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
PRECISION ASSEMBLY |  |  |  |  | HR | 4718 | 0.25 | 1179.5 | 63 | 74308.5 |  |  |  | 0 |  | 0
PLATING & CLEANING WC475 |  |  |  |  | HR | 4718 | 0.1 | 471.8 | 109 | 51426.2 |  |  |  | 0 |  | 0
PLATING & CLEANING |  |  |  |  | HR | 24000 | 0.01 | 240 | 109 | 26160 |  |  |  | 0 |  | 0
MECHANICAL TECHS |  |  |  |  | HR | 4718 | 1 | 4718 | 39 | 184002 |  |  |  | 0 |  | 0
SUBTOTAL |  |  |  | 4650624 | [5 empty] | 964142.7 | [5 empty] | 434000
TOTAL B&H |  |  |  | 5614766.7
TOTAL ED&I |  |  |  | 434000
PROJECT TOTAL |  |  |  | 6048766.7
Includes the cost of two 25 l/s, one on the wrap aroung mode converter and one just after the valve.

## ML Acc.Manifold
NLC ENGINEERING ESTIMATE
PROJECT: NLC Accelerator Vacuum Manifold and Processing 500 GeV |  |  |  |  | DATE: 3/9/99
ENGINEER: J. Weinberg |  |  |  | REVISION:1
[6 empty] | B&H | [7 empty] | ED&I
|  | MATERIAL | [5 empty] | LABOR
ITEM | MEAS | # UNITS | UNIT COST | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL | MEAS | # UNITS | UNIT HRS | TOTAL HRS | $/HR | TOTAL
Vacuum Manifold
2" S.St. Tube | m | 19010 | 8.2 | 155882 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Bellows | ea | 57024 | 35 | 1995840 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
25 l/s ion pump | ea | 4968 | 1200 | 5961600 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Eyelets 20 per Acc. | ea | 95000 | 1 | 95000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Eyelet adaptors and blanks | ea | 9504 | 10 | 95040 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Tin seals | ea | 20000 | 1 | 20000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Tin seal clamps | ea | 10000 | 50 | 500000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Beam Line Gauge tubes | ea | 92 | 600 | 55200
Beam line isolation valves | ea | 46 | 4000 | 184000 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Vacuum Processing
Tech labor for Bakeout |  |  |  | 0 | 10 techs, 2 yrs | 4968 | 10 | 49680 | 39 | 1937520 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 | Vac. Engr. |  |  | 6000 | 55 | 330000
|  |  |  | 0 |  |  |  | 0 |  | 0 | Designer |  |  | 9432 | 52 | 490464
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
ENGINEERING | [7 empty] | 0 |  | 0 | [5 empty] | 0
DESIGN | [7 empty] | 0 |  | 0 |  |  |  | 0 |  | 0
MECHANICAL FAB |  |  |  |  | HR | 4752 | 0.5 | 2376 | 77 | 182952 |  |  |  | 0 |  | 0
QC |  |  |  |  | HR | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
PRECISION ASSEMBLY |  |  |  |  | HR | 0 | 0 | 0 | 63 | 0 |  |  |  | 0 |  | 0
PLATING & CLEANING |  |  |  |  | HR | 100000 | 0.1 | 10000 | 109 | 1090000 |  |  |  | 0 |  | 0
WELDING |  |  |  |  | HR | 40000 | 0.25 | 10000 | 77 | 770000
MECHANICAL TECHS |  |  |  |  | HR | 4752 | 1 | 4752 | 39 | 185328 |  |  |  | 0 |  | 0
SUBTOTAL |  |  |  | 9062562 | [5 empty] | 4165800 | [5 empty] | 820464
TOTAL B&H |  |  |  | 13228362
TOTAL ED&I |  |  |  | 820464
PROJECT TOTAL |  |  |  | 14048826
Includes the cost of processing the accelerator structure together with the RF Feed and vacuum manifold.
Ion pumps, beamline valves and gauges are included.